DevOS POC Product Backlog & Sprint Plan

Version 1.0 • 8-Sprint Vertical-Slice Delivery Plan

Purpose: Translate the DevOS POC Architecture and Software Change Workflow into an executable product backlog and sprint plan. The plan is designed to prove the core DevOS proposition through one complete Software Change Workflow before expanding into additional workflows, governance, cost management and advanced peripherals.

# 1. Executive Summary

The POC will be delivered as an 8-sprint programme, assuming two-week sprints and a small cross-functional engineering team. The plan deliberately uses vertical slices: every sprint should leave DevOS more capable of executing the reference Software Change Workflow. Platform work is pulled forward only when it is needed by the next workflow capability.

The target outcome at the end of Sprint 8 is a controlled pilot in which a real software change can progress from work item to release evidence with AI agents, human approvals, repository/CI integrations, traceability and basic security controls.

# 2. Delivery Principles

Prioritise the reference workflow over platform completeness.

Build the smallest reusable primitive that enables the next workflow stage.

Keep published workflow definitions immutable.

Keep agent authority outside the model.

Use real integrations as early as practical.

Every sprint ends with demonstrable functionality.

Do not build deferred peripherals until the vertical slice works.

Prefer boring, durable infrastructure over premature distributed architecture.

Use acceptance tests to define 'done', not demo quality alone.

# 3. POC Outcome

| Dimension | Target outcome |
| --- | --- |
| Workflow | Complete Software Change Workflow executes end-to-end |
| Agents | Requirements, architecture/planning, development, QA/review capabilities work through a common runtime |
| Artifacts | PRD, technical design, implementation plan and evidence are versioned and traceable |
| Human control | Planning and release approval gates are enforced |
| Tools | Issue tracker, Git and build/test/CI capabilities are integrated |
| Security | Tenant/project scope, agent authority and tool policy are enforced |
| Recovery | Retry, failure and rework paths operate safely |
| UX | User can monitor and control a run |
| Operations | Logs, events and basic metrics allow diagnosis |

# 4. Team Assumption

| Role | Primary responsibility |
| --- | --- |
| Product Owner | Prioritisation, workflow decisions, acceptance |
| Tech Lead | Architecture, technical decisions, code quality |
| Backend/Platform Engineer | Workflow, API, data, integrations |
| Full-stack Engineer | UI, API integration, workflow experience |
| AI/Agent Engineer | Agent runtime, prompts/contracts, provider adapters |
| QA Engineer | Test strategy, E2E, security and acceptance |
| DevOps/Platform | CI/CD, deployment, observability |

A smaller team can combine roles. The plan is capability-based rather than dependent on seven separate people.

# 5. Estimation Model

Use relative story points for planning. Points are not hours and should be calibrated by the actual team after Sprint 1.

| Size | Meaning |
| --- | --- |
| 1 | Trivial/configuration |
| 2 | Small, well understood |
| 3 | Moderate |
| 5 | Complex but bounded |
| 8 | Large/uncertain; should usually be split |
| 13 | Too large for a sprint; split before commitment |

The sprint plan uses capacity as a guide, not a promise. Unfinished work returns to the backlog and is re-estimated.

# 6. Priority Model

| Priority | Meaning |
| --- | --- |
| P0 | Required to prove the POC |
| P1 | Important for a credible pilot |
| P2 | Useful but can be deferred |
| P3 | Post-POC |

# 7. Epic Map

| Epic | Outcome | Priority |
| --- | --- | --- |
| E1 | Platform Foundation | P0 |
| E2 | Identity & Project Context | P0 |
| E3 | Workflow Definition & Runtime | P0 |
| E4 | Artifact & Provenance | P0 |
| E5 | Knowledge & Context | P0 |
| E6 | Agent Runtime | P0 |
| E7 | Approval & Policy | P0 |
| E8 | Tool Gateway & Integrations | P0 |
| E9 | Development Workflow | P0 |
| E10 | Validation & Review | P0 |
| E11 | Release & Closure | P0 |
| E12 | UI/UX | P0 |
| E13 | Observability | P1 |
| E14 | Security Hardening | P1 |
| E15 | POC Pilot & Documentation | P1 |
| E16 | Future Governance/Cost/Analytics | P3 |

# 8. Product Backlog — Platform Foundation

| ID | Story | Pts | Pri | Acceptance summary |
| --- | --- | --- | --- | --- |
| DEVOS-001 | Create application repository and engineering standards | 3 | P0 | Build, test and lint run in CI |
| DEVOS-002 | Create backend service skeleton | 3 | P0 | Service starts with health endpoint and config |
| DEVOS-003 | Create React application shell | 3 | P0 | Authenticated shell can render project context |
| DEVOS-004 | Create PostgreSQL schema/migration framework | 3 | P0 | Migrations run cleanly in dev/staging |
| DEVOS-005 | Create environment configuration and secret references | 3 | P0 | No secrets committed; environments configurable |
| DEVOS-006 | Create structured logging/correlation IDs | 3 | P0 | Requests/jobs carry correlation IDs |
| DEVOS-007 | Create deployment pipeline | 5 | P0 | Application deploys repeatably to development |
| DEVOS-008 | Create error handling conventions | 2 | P0 | API/worker failures produce consistent errors |

# 9. Product Backlog — Identity & Project Context

| ID | Story | Pts | Pri | Acceptance summary |
| --- | --- | --- | --- | --- |
| DEVOS-010 | Integrate OIDC-compatible authentication | 5 | P0 | User can sign in/out and session is validated |
| DEVOS-011 | Create organisation/project model | 3 | P0 | Projects belong to organisation |
| DEVOS-012 | Create project membership and roles | 5 | P0 | Authorised roles control project actions |
| DEVOS-013 | Apply project scope to API/data access | 5 | P0 | Cross-project access is denied |
| DEVOS-014 | Create project selection UX | 2 | P0 | User can select authorised project |
| DEVOS-015 | Create basic administration view | 3 | P1 | Admin can manage project membership |

# 10. Product Backlog — Workflow Definition & Runtime

| ID | Story | Pts | Pri | Acceptance summary |
| --- | --- | --- | --- | --- |
| DEVOS-020 | Define workflow schema | 5 | P0 | Schema supports nodes, edges, inputs, outputs and policies |
| DEVOS-021 | Persist workflow definitions | 3 | P0 | Draft definitions persist |
| DEVOS-022 | Create immutable workflow versions | 5 | P0 | Published version cannot be mutated |
| DEVOS-023 | Create workflow run/state model | 5 | P0 | Run/task states persist across process restarts |
| DEVOS-024 | Create durable job dispatch | 5 | P0 | Tasks execute asynchronously and survive restart |
| DEVOS-025 | Implement sequential transitions | 3 | P0 | Tasks advance based on successful completion |
| DEVOS-026 | Implement conditions/branching | 5 | P0 | Pass/fail routes are deterministic |
| DEVOS-027 | Implement retry policy | 3 | P0 | Transient failures retry within limits |
| DEVOS-028 | Implement pause/resume/cancel | 5 | P0 | Authorised user can control active run |
| DEVOS-029 | Implement workflow run UI | 5 | P0 | User sees stages/tasks/status |
| DEVOS-030 | Implement workflow validation | 5 | P0 | Invalid workflows cannot publish |
| DEVOS-031 | Implement workflow version diff | 3 | P1 | User can compare versions |

# 11. Product Backlog — Artifacts & Provenance

| ID | Story | Pts | Pri | Acceptance summary |
| --- | --- | --- | --- | --- |
| DEVOS-040 | Create artifact metadata model | 3 | P0 | Artifact types/status/ownership persist |
| DEVOS-041 | Create artifact version model | 5 | P0 | Every update creates traceable version |
| DEVOS-042 | Add object storage adapter | 3 | P0 | Large content stored outside DB |
| DEVOS-043 | Create artifact viewer | 5 | P0 | User can read current/versioned artifact |
| DEVOS-044 | Create artifact relationships | 5 | P0 | Upstream/downstream relationships are navigable |
| DEVOS-045 | Create artifact provenance | 3 | P0 | Workflow/task/agent/source references recorded |
| DEVOS-046 | Create artifact validation state | 3 | P1 | Artifact can be draft/validated/approved |

# 12. Product Backlog — Knowledge & Context

| ID | Story | Pts | Pri | Acceptance summary |
| --- | --- | --- | --- | --- |
| DEVOS-050 | Create project knowledge source model | 3 | P0 | Sources can be registered |
| DEVOS-051 | Implement repository/context retrieval | 5 | P0 | Relevant authorised content can be retrieved |
| DEVOS-052 | Implement artifact retrieval | 3 | P0 | Prior approved artifacts can be used as context |
| DEVOS-053 | Create context manifest | 5 | P0 | Each material agent execution records sources |
| DEVOS-054 | Enforce knowledge permissions | 5 | P0 | Agent cannot retrieve unauthorised project data |
| DEVOS-055 | Create context inspection UI | 3 | P1 | User can inspect sources used |

# 13. Product Backlog — Agent Runtime

| ID | Story | Pts | Pri | Acceptance summary |
| --- | --- | --- | --- | --- |
| DEVOS-060 | Create agent definition model | 3 | P0 | Agent role/version/config persist |
| DEVOS-061 | Create LLM provider abstraction | 5 | P0 | Agent code does not depend on one provider |
| DEVOS-062 | Implement agent execution service | 5 | P0 | Agent execution is durable and observable |
| DEVOS-063 | Implement controlled prompt/context builder | 5 | P0 | Only authorised context enters execution |
| DEVOS-064 | Implement structured output validation | 5 | P0 | Invalid agent output cannot publish |
| DEVOS-065 | Implement requirements agent | 5 | P0 | Produces PRD artifact |
| DEVOS-066 | Implement architect agent | 5 | P0 | Produces technical design |
| DEVOS-067 | Implement planning agent | 5 | P0 | Produces implementation plan |
| DEVOS-068 | Create agent execution UI | 3 | P1 | User can inspect inputs/actions/output/evidence |
| DEVOS-069 | Add uncertainty/insufficient-information handling | 3 | P0 | Unknowns are explicit; no invented facts |

# 14. Product Backlog — Approval & Policy

| ID | Story | Pts | Pri | Acceptance summary |
| --- | --- | --- | --- | --- |
| DEVOS-070 | Create policy model | 5 | P0 | Project policies persist and are evaluated |
| DEVOS-071 | Create agent authority envelope | 5 | P0 | Execution has bounded project/capability/resource scope |
| DEVOS-072 | Create tool capability policy | 5 | P0 | Unauthorised capability is denied |
| DEVOS-073 | Create approval request model | 3 | P0 | Approval is tied to exact action/scope |
| DEVOS-074 | Create approval centre UI | 5 | P0 | Approver sees evidence/risk/target |
| DEVOS-075 | Enforce planning approval gate | 3 | P0 | Development cannot start without approval |
| DEVOS-076 | Enforce release approval gate | 3 | P0 | Configured release cannot proceed without approval |
| DEVOS-077 | Create audit record for policy/approval decisions | 3 | P0 | Decision is attributable and durable |

# 15. Product Backlog — Tool Gateway & Integrations

| ID | Story | Pts | Pri | Acceptance summary |
| --- | --- | --- | --- | --- |
| DEVOS-080 | Create tool definition/capability model | 3 | P0 | Tools expose explicit capabilities |
| DEVOS-081 | Create tool gateway | 5 | P0 | All material tool actions pass through gateway |
| DEVOS-082 | Create integration credential reference model | 3 | P0 | Credentials represented by references |
| DEVOS-083 | Create issue tracker adapter | 5 | P0 | Read work item and update status |
| DEVOS-084 | Create Git repository adapter | 5 | P0 | Read/search repository |
| DEVOS-085 | Create Git branch/commit adapter | 5 | P0 | Controlled feature branch changes |
| DEVOS-086 | Create pull request adapter | 3 | P0 | PR can be created |
| DEVOS-087 | Create test/build adapter | 5 | P0 | Build/tests execute and return evidence |
| DEVOS-088 | Create CI adapter | 5 | P1 | Pipeline can be triggered/read |
| DEVOS-089 | Create notification adapter | 2 | P1 | Approval/failure notifications delivered |

# 16. Product Backlog — Development Workflow

| ID | Story | Pts | Pri | Acceptance summary |
| --- | --- | --- | --- | --- |
| DEVOS-090 | Implement development agent contract | 5 | P0 | Consumes approved planning package |
| DEVOS-091 | Implement secure workspace creation | 5 | P0 | Agent runs in isolated workspace |
| DEVOS-092 | Implement repository context for development | 5 | P0 | Agent receives relevant code/context |
| DEVOS-093 | Implement controlled code modification | 5 | P0 | Changes limited to authorised workspace |
| DEVOS-094 | Implement branch creation | 3 | P0 | Feature branch created |
| DEVOS-095 | Implement commit creation | 3 | P0 | Commit is attributable |
| DEVOS-096 | Implement PR creation | 3 | P0 | PR references work item |
| DEVOS-097 | Implement development evidence | 3 | P0 | Files/commit/PR references recorded |

# 17. Product Backlog — Validation & Review

| ID | Story | Pts | Pri | Acceptance summary |
| --- | --- | --- | --- | --- |
| DEVOS-100 | Implement build task | 3 | P0 | Build result captured |
| DEVOS-101 | Implement test task | 5 | P0 | Test results captured as evidence |
| DEVOS-102 | Implement static analysis task | 3 | P1 | Analysis result captured |
| DEVOS-103 | Implement security validation task | 5 | P1 | Blocking findings prevent progression |
| DEVOS-104 | Implement review agent | 5 | P0 | Review produces structured findings |
| DEVOS-105 | Implement review decision state | 3 | P0 | Pass/fail state drives workflow |
| DEVOS-106 | Implement rework loop | 5 | P0 | Findings route back to development |
| DEVOS-107 | Implement review evidence artifact | 3 | P0 | Evidence links findings to code/tests |

# 18. Product Backlog — Release & Closure

| ID | Story | Pts | Pri | Acceptance summary |
| --- | --- | --- | --- | --- |
| DEVOS-110 | Implement release readiness checklist | 3 | P0 | Required evidence checked |
| DEVOS-111 | Create release evidence artifact | 3 | P0 | Release package is traceable |
| DEVOS-112 | Create controlled deployment adapter | 5 | P0 | Deployment only allowed by policy |
| DEVOS-113 | Implement post-release validation | 3 | P1 | Release result verified |
| DEVOS-114 | Implement workflow closure | 3 | P0 | Work item/run/evidence linked and closed |
| DEVOS-115 | Implement rollback capability contract | 5 | P1 | Rollback path defined where supported |

# 19. Product Backlog — UI/UX

| ID | Story | Pts | Pri | Acceptance summary |
| --- | --- | --- | --- | --- |
| DEVOS-120 | Home/project dashboard | 5 | P0 | User sees active work and attention items |
| DEVOS-121 | Work item view | 3 | P0 | Work item and workflow status visible |
| DEVOS-122 | Workflow run visualisation | 5 | P0 | Stages/tasks/status visible |
| DEVOS-123 | Task detail view | 3 | P0 | Inputs/output/error/retry visible |
| DEVOS-124 | Artifact viewer | 3 | P0 | Artifacts readable/versioned |
| DEVOS-125 | Approval centre | 5 | P0 | Pending decisions actionable |
| DEVOS-126 | Agent execution view | 3 | P1 | Agent actions/evidence visible |
| DEVOS-127 | Integration status | 3 | P1 | Connections/health visible |
| DEVOS-128 | Basic workflow definition editor | 5 | P1 | Reference workflow configurable |
| DEVOS-129 | Search | 3 | P1 | Authorised resources searchable |

# 20. Product Backlog — Observability & Security Hardening

| ID | Story | Pts | Pri | Acceptance summary |
| --- | --- | --- | --- | --- |
| DEVOS-130 | Create outbox/event mechanism | 5 | P0 | Domain events reliably published |
| DEVOS-131 | Add audit trail | 5 | P0 | Material actions searchable |
| DEVOS-132 | Add workflow/agent/tool metrics | 3 | P1 | Basic operational metrics visible |
| DEVOS-133 | Add distributed correlation/tracing | 3 | P1 | Run/task/tool chain traceable |
| DEVOS-134 | Tenant isolation test suite | 5 | P0 | Cross-tenant access tests pass |
| DEVOS-135 | Agent privilege escalation tests | 5 | P0 | Agent cannot exceed authority |
| DEVOS-136 | Secret leakage/redaction tests | 5 | P0 | Secrets absent from logs/context |
| DEVOS-137 | Prompt injection security tests | 5 | P1 | Malicious content cannot grant authority |
| DEVOS-138 | Tool replay/idempotency tests | 3 | P0 | Repeated action does not duplicate side effect |
| DEVOS-139 | Failure/recovery test suite | 5 | P1 | Worker/provider failures recover safely |

# 21. Product Backlog — Pilot

| ID | Story | Pts | Pri | Acceptance summary |
| --- | --- | --- | --- | --- |
| DEVOS-150 | Create POC environment runbook | 3 | P1 | Team can deploy/operate environment |
| DEVOS-151 | Create user/admin runbook | 2 | P1 | Pilot users can be onboarded |
| DEVOS-152 | Create workflow operator runbook | 3 | P1 | Failures/retries/approvals documented |
| DEVOS-153 | Create POC acceptance test pack | 5 | P1 | E2E scenarios automated/documented |
| DEVOS-154 | Run controlled pilot | 5 | P1 | Real change completes successfully |
| DEVOS-155 | Capture pilot findings | 3 | P1 | Prioritised improvements recorded |
| DEVOS-156 | Create post-POC roadmap | 3 | P1 | Next workflows/platform evolution defined |

# 22. Sprint Strategy

Eight two-week sprints are recommended. The first six build the core vertical slice; Sprint 7 hardens it; Sprint 8 runs the pilot and converts findings into the next roadmap.

| Sprint | Theme | Primary outcome |
| --- | --- | --- |
| 1 | Foundation + Workflow Skeleton | Deployable shell and durable dummy workflow |
| 2 | Artifacts + Agent Runtime | AI-generated engineering artifacts |
| 3 | Planning Gate + Knowledge | Approved planning package |
| 4 | Git + Development | Real controlled code change/PR |
| 5 | Validation + Review | Test/review/rework loop |
| 6 | Release + Complete Flow | End-to-end software change |
| 7 | Security + Observability | Pilot-grade reliability/security |
| 8 | Pilot + Optimisation | Real-user pilot and next roadmap |

# 23. Sprint 1 — Foundation + Workflow Skeleton

| Item | Pts |
| --- | --- |
| DEVOS-001 | 3 |
| DEVOS-002 | 3 |
| DEVOS-003 | 3 |
| DEVOS-004 | 3 |
| DEVOS-005 | 3 |
| DEVOS-006 | 3 |
| DEVOS-007 | 5 |
| DEVOS-010 | 5 |
| DEVOS-011 | 3 |
| DEVOS-014 | 2 |
| DEVOS-020 | 5 |
| DEVOS-021 | 3 |
| DEVOS-022 | 5 |
| DEVOS-023 | 5 |
| DEVOS-024 | 5 |
| DEVOS-025 | 3 |
| DEVOS-029 | 5 |

Sprint objective: A user can authenticate, select a project, start a simple workflow and watch durable tasks execute.

Exit criteria: deployable system; authenticated project context; durable workflow run; restart recovery; basic run UI.

# 24. Sprint 2 — Artifacts + Agent Runtime

| Item | Pts |
| --- | --- |
| DEVOS-040 | 3 |
| DEVOS-041 | 5 |
| DEVOS-042 | 3 |
| DEVOS-043 | 5 |
| DEVOS-045 | 3 |
| DEVOS-050 | 3 |
| DEVOS-051 | 5 |
| DEVOS-052 | 3 |
| DEVOS-053 | 5 |
| DEVOS-060 | 3 |
| DEVOS-061 | 5 |
| DEVOS-062 | 5 |
| DEVOS-063 | 5 |
| DEVOS-064 | 5 |
| DEVOS-065 | 5 |
| DEVOS-066 | 5 |
| DEVOS-067 | 5 |
| DEVOS-069 | 3 |

Sprint objective: DevOS can execute agent tasks that create versioned PRD, technical design and implementation-plan artifacts.

Exit criteria: three artifact-producing agents execute through the workflow and outputs are inspectable with provenance.

# 25. Sprint 3 — Knowledge + Planning Approval

| Item | Pts |
| --- | --- |
| DEVOS-054 | 5 |
| DEVOS-055 | 3 |
| DEVOS-070 | 5 |
| DEVOS-071 | 5 |
| DEVOS-072 | 5 |
| DEVOS-073 | 3 |
| DEVOS-074 | 5 |
| DEVOS-075 | 3 |
| DEVOS-077 | 3 |
| DEVOS-121 | 3 |
| DEVOS-124 | 3 |
| DEVOS-125 | 5 |
| DEVOS-126 | 3 |

Sprint objective: The planning package is permission-aware, reviewable and must be approved before development.

Exit criteria: planning approval is enforced server-side; rejection returns to a defined stage; context provenance is visible.

# 26. Sprint 4 — Git + Development

| Item | Pts |
| --- | --- |
| DEVOS-080 | 3 |
| DEVOS-081 | 5 |
| DEVOS-082 | 3 |
| DEVOS-084 | 5 |
| DEVOS-085 | 5 |
| DEVOS-086 | 3 |
| DEVOS-090 | 5 |
| DEVOS-091 | 5 |
| DEVOS-092 | 5 |
| DEVOS-093 | 5 |
| DEVOS-094 | 3 |
| DEVOS-095 | 3 |
| DEVOS-096 | 3 |
| DEVOS-097 | 3 |

Sprint objective: An approved plan can be executed by a development agent to produce a controlled repository change and PR.

Exit criteria: real repository branch/commit/PR exists; tool actions are authorised and audited.

# 27. Sprint 5 — Validation + Review + Rework

| Item | Pts |
| --- | --- |
| DEVOS-100 | 3 |
| DEVOS-101 | 5 |
| DEVOS-104 | 5 |
| DEVOS-105 | 3 |
| DEVOS-106 | 5 |
| DEVOS-107 | 3 |
| DEVOS-028 | 5 |
| DEVOS-026 | 5 |
| DEVOS-027 | 3 |
| DEVOS-122 | 5 |
| DEVOS-123 | 3 |

Sprint objective: DevOS can validate a change, identify review findings and automatically route fixable findings back to development.

Exit criteria: both pass and fail/rework paths are demonstrated; retries are bounded and visible.

# 28. Sprint 6 — Release + Complete Vertical Slice

| Item | Pts |
| --- | --- |
| DEVOS-083 | 5 |
| DEVOS-087 | 5 |
| DEVOS-089 | 2 |
| DEVOS-076 | 3 |
| DEVOS-110 | 3 |
| DEVOS-111 | 3 |
| DEVOS-112 | 5 |
| DEVOS-113 | 3 |
| DEVOS-114 | 3 |
| DEVOS-115 | 5 |
| DEVOS-130 | 5 |
| DEVOS-131 | 5 |
| DEVOS-120 | 5 |

Sprint objective: Complete the Software Change Workflow from work item to controlled release evidence.

Exit criteria: one real change can complete end-to-end in a controlled environment; all material actions have evidence.

# 29. Sprint 7 — Security + Observability Hardening

| Item | Pts |
| --- | --- |
| DEVOS-012 | 5 |
| DEVOS-013 | 5 |
| DEVOS-134 | 5 |
| DEVOS-135 | 5 |
| DEVOS-136 | 5 |
| DEVOS-138 | 3 |
| DEVOS-139 | 5 |
| DEVOS-103 | 5 |
| DEVOS-132 | 3 |
| DEVOS-133 | 3 |
| DEVOS-127 | 3 |
| DEVOS-150 | 3 |

Sprint objective: Make the vertical slice safe and diagnosable enough for a controlled pilot.

Exit criteria: security tests pass; authority boundaries are demonstrated; failure recovery works; operator runbook exists.

# 30. Sprint 8 — Pilot + Optimisation

| Item | Pts |
| --- | --- |
| DEVOS-128 | 5 |
| DEVOS-129 | 3 |
| DEVOS-152 | 3 |
| DEVOS-153 | 5 |
| DEVOS-154 | 5 |
| DEVOS-155 | 3 |
| DEVOS-156 | 3 |
| DEVOS-137 | 5 |
| DEVOS-151 | 2 |

Sprint objective: Run a real controlled pilot, capture evidence and decide what DevOS should build next.

Exit criteria: pilot users complete the workflow; findings are categorised; next roadmap is approved.

# 31. Sprint Dependencies

| Dependency | Why |
| --- | --- |
| Foundation → Workflow | Runtime requires persistence and deployment |
| Workflow → Artifacts | Agent outputs need durable artifact contracts |
| Artifacts → Agents | Agent tasks need output targets |
| Knowledge → Agents | Agents need authorised context |
| Approval → Development | Development must be blocked until planning gate |
| Tool Gateway → Git | Development actions must be policy controlled |
| Development → Validation | Tests need a real code change |
| Validation → Review | Review needs evidence |
| Review → Release | Release readiness depends on review |
| Security/Observability → Pilot | Pilot requires safe operation |

# 32. Critical Path

Foundation

↓

Workflow Runtime

↓

Artifacts

↓

Agent Runtime

↓

Planning Approval

↓

Git / Development

↓

Validation

↓

Review / Rework

↓

Release

↓

Pilot

# 33. Sprint Ceremonies

| Ceremony | Purpose |
| --- | --- |
| Sprint Planning | Select highest-value stories that support sprint objective |
| Daily Sync | Identify blockers and coordinate delivery |
| Backlog Refinement | Clarify/split upcoming stories |
| Sprint Review | Demonstrate working DevOS capability |
| Retrospective | Improve delivery and engineering process |
| Architecture/Design Review | Resolve material cross-cutting decisions as needed |

# 34. Definition of Ready

Story has clear user/business outcome.

Acceptance criteria are testable.

Dependencies are identified.

Security implications are known.

Required design decisions are resolved or explicitly tracked.

Story is small enough for a sprint.

External integration assumptions are identified.

# 35. Definition of Done

Code implemented and reviewed.

Automated tests pass.

Relevant acceptance criteria pass.

Security controls are tested where applicable.

Observability is included for runtime behaviour.

Database migrations/configuration are complete.

Documentation/runbook updated where needed.

Feature is deployed to the target environment.

Product Owner accepts the story.

# 36. POC End-to-End Acceptance Test

Create a realistic feature work item.

Start the Software Change Workflow.

Verify intake/discovery output.

Verify PRD is generated and versioned.

Verify technical design is generated and versioned.

Verify implementation plan is generated and versioned.

Reject the planning package once and verify controlled rework.

Approve the planning package.

Verify development agent authority.

Verify branch/commit/PR creation.

Verify build/tests execute.

Introduce a controlled validation failure.

Verify rework loop.

Verify review passes after correction.

Verify release readiness.

Reject release once and verify release is blocked.

Approve release.

Verify controlled release/post-release validation.

Verify final evidence and traceability.

# 37. Key Product Metrics for the POC

| Metric | Why it matters |
| --- | --- |
| Workflow completion rate | Basic reliability |
| Median workflow cycle time | End-to-end speed |
| Planning cycle time | Value of AI planning |
| Agent success rate | Runtime reliability |
| Rework rate | Quality of generated implementation |
| Human approval wait time | Human bottleneck |
| Tool failure rate | Integration reliability |
| Automation rate | Amount of work performed without intervention |
| Cost/run | Baseline for future cost controls |
| Traceability completeness | Auditability |

# 38. What We Will Not Optimise Yet

Lowest possible model cost

Maximum agent autonomy

High-volume event throughput

Multi-region availability

Full enterprise SSO lifecycle

Advanced RAG optimisation

Fine-grained cost allocation

Organisation-wide engineering analytics

Large workflow marketplace

Dozens of external integrations

# 39. Backlog Prioritisation After Each Sprint

At the end of each sprint, re-rank the remaining backlog using four questions:

Does this directly enable the next part of the reference workflow?

Does this remove a demonstrated reliability/security risk?

Does this improve the user experience of the reference workflow?

Can this be deferred without invalidating the POC?

If the answer to all four is 'no', defer the item.

# 40. Expected POC Milestones

| Milestone | Target sprint |
| --- | --- |
| M1 — DevOS deployable | 1 |
| M2 — Durable workflow execution | 1 |
| M3 — AI planning artifacts | 2 |
| M4 — Human-controlled planning | 3 |
| M5 — Real repository change | 4 |
| M6 — Automated validation/rework | 5 |
| M7 — Complete software change flow | 6 |
| M8 — Pilot-grade security/observability | 7 |
| M9 — Controlled real-user pilot | 8 |

# 41. Post-POC Roadmap Themes

| Theme | Examples |
| --- | --- |
| Workflow Expansion | Incident, release, dependency, documentation workflows |
| Workflow Designer | Full visual authoring |
| Governance | Policy-as-code, compliance, approvals |
| Cost | Model/tool budgets, attribution, optimisation |
| Engineering Intelligence | DORA, quality, bottleneck analytics |
| Agent Platform | Agent marketplace, evaluation, lifecycle |
| Knowledge | Enterprise indexing, graph, advanced retrieval |
| Autonomy | Risk-based reduction of human gates |
| Integrations | More Git/CI/Jira/cloud providers |

# 42. Product Decision Gate After Sprint 8

Do not automatically continue building features after the pilot. Hold a product/architecture gate and answer:

Did DevOS reliably complete the reference workflow?

Did users trust the generated artifacts?

Did developers receive better implementation inputs?

Where did humans still need to intervene?

Which agents produced useful outputs?

Which integrations were unreliable?

Where did security controls block legitimate work?

What was the real cost per workflow?

Which next workflow has the highest value?

The answers should determine the next product backlog.

# 43. Final Recommendation

The eight-sprint plan is intentionally aggressive but achievable only if scope is protected. The team should resist turning the POC into a general-purpose AI development platform before the reference workflow works.

The strongest implementation strategy is to make Sprint 6 the first major success milestone: a complete software change should be executable end-to-end. Sprints 7 and 8 then convert that capability from a technical demonstration into a controlled pilot.

Once the pilot proves the core loop, DevOS can safely expand outward into the Workflow Designer, additional workflows, governance, cost management, engineering intelligence and higher levels of autonomy.